## Tabellenblatt1
Use Case | Estimated time (min) | Spent Time (min) | Function Points
Delete Group | 180 | 260 | 21.6
Create Proposal | 546 | 340 | 9.68
Manage Group | 30390 | 32016 | 76.5
Manage Group memberships | 5910 | 4747 | 111.6
New Use Case |  | Calculated Time (min)
Rate Proposal | - | 9406.8966 | 27.28
Filter View By Activities | - | 6979.3103 | 20.24
Sum of old Ucs | 37026 | 37363 | 219.38
Sum Spent Time / Sum Points | 170.3118
Delete Group | RET | DET | FTR | Resulting Complexity | RET | DET | FTR
External Inputs | x | 1 | 1 | Low | - | delete button | group database
External Output | x | 1 | 2 | Low | - | confirmation popup | group database, account database
External Querie | x | 1 | 2 | Low | - | group edit button | group database, account database
Internal Logical Files | 2 | 6 | x | Low | group repository, membership repository | group id, group name, membership id, group, user, role | -
External Interface Files | 0 | 0 | x | Low | - |  | -
CRUD Manage Group | RET | DET | FTR | Resulting Complexity | RET | DET | FTR
External Inputs | x | 14 | 2 | Avg | - | create group button, edit group button, group name input (2x), confirm button (3x), cancel button (2x), revoke admin role, kick member, x-button (3x) | group database, account database
External Output | x | 3 | 2 | Low | - | create group popup, group settings, add member popup | group database, account database
External Querie | x | 1 | 1 | Low | - | change group | group database
Internal Logical Files | 2 | 6 | x | Low | group repository, membership repository | group id, group name, membership id, group, user, role | -
External Interface Files | 0 | 0 | x | Low | - | - | -
Manage group memberships | RET | DET | FTR | Resulting Complexity | RET | DET | FTR
External Inputs | x | 14 | 3 | High | - | e-mail address (2x), grant admin role (3x) , add member button, cancel invitation (3x), cancel button (2x), invite member, accept icon, decline icon | group database, account database, invitation database
External Output | x | 4 | 3 | Low | - | create group popup, group settings, add member popup, remaining invitations list | group database, account database, invitation database
External Querie | x | 1 | 2 | Low | - | hubpage: remaining invitations list | group database, invitation database
Internal Logical Files | 3 | 9 | x | Low | group repository, membership repository, invitation repository | group id, group name, membership id, group, user, role, recipient, emitter, group, invitation id | -
External Interface Files | 0 | 0 | x | Low | - | - | -
Upcomming UCs
Create Proposal | RET | DET | FTR | Resulting Complexity | RET | DET | FTR
External Inputs | x | 10 | 2 | Avg | - | add proposal button, activity type, proposal name, straße, stadt, plz, add groups, confirm button, cancel button, x-button | rating database, group database
External Output | x | 1 | 1 | Low | - | add proposal popup | rating database
External Querie | x | 1 | 2 | Low | - | rating list | rating database, group database
Internal Logical Files | 2 | 7 | x | Low | proposal repository, groupProposal repository | proposalld, activity type, name, address, groupProposalId, group, proposal | -
External Interface Files | 0 | 0 | x | Low | - | - | -
Rate Proposal | RET | DET | FTR | Resulting Complexity | RET | DET | FTR
External Inputs | x | 1 | 1 | Low | - | thumbs rating | rating database
External Output | x | 1 | 2 | Low | - | best of rating list | rating database, group database
External Querie | x | 2 | 2 | Low | - | rating list, best of rating list | rating database, group database
Internal Logical Files | 3 | 11 | x | Low | rating repository, groupProposal repository, proposal repository | rating id, user, rating value, group proposal id, proposal id, name, address, activity type, group proposal id, group id, proposal id | -
External Interface Files | 0 | 0 | x | Low | - | - | -
Filter View by activites | RET | DET | FTR | Resulting Complexity | RET | DET | FTR
External Inputs | x | 2 | 1 | Low | - | activity icons, reset button | rating database
External Output | x | 2 | 2 | Low | - | filtered best of rating list, filtered rating list | rating database, group database
External Querie | x | 2 | 2 | Low | - | best of rating list, rating list | rating databse, group database
Internal Logical Files | 3 | 11 | x | Low | rating repository, proposal repository, groupProposal repository | rating id, user, rating value, group proposal id, proposal id, name, address, activity type, group proposal id, group id, proposal id | -
External Interface Files | 0 | 0 | x | Low | - | - | -