## Tabelle1
Risk name | Risk Description | Risk Probability of Occurence | Risk Impact | Risk Factor | Risk Mitigation | Person in Charge of Tracking
Project time management | planning not precisly enough, too much time for one use case, not observing the remaining time | known risk | 7 | High | plan sprints in advance -> distribute epics/user stories roughly on the remaining sprints; include capacity of team members in planning; keep an eye on deadlines | Lucie
Underestimated complexity | tasks are more difficult than thought | known risk | 4 | High | research of frameworks and technology in use; risk premium on story points/time estimation; retrospective to learn from wrong estimation of complexity | Patrick
Internal team conflicts | team work is not going well, lack of respect, tensions between members, missing/bad communication | predictable but uncertain | 9 | High | retrospective; frequently meetings for agreements; team activities | Tom
Fundamental issues in code base | throughout the project realisation that you made architectural mistakes while implementing the code base | predictable but uncertain | 9 | High | code reviews; early and regularly refactoring; pair programming | Patrick
Loss/absence of a team member | illness, quitting studies (exmatriculation) | unpredictable | 10 | Medium | Don't drink and smoke! :D ; early communication if quitting studies | all
Work environment failure | memory size too small, operating system corrupts, memory loss, internet access problems | unpredictable | 3 | Low | regularly backups; working in the cloud; commit and push after work; virus protection | all