## Tabellenblatt1
Use Case | Estimated time | Spent Time (min) | Function Points
Delete Group | 9h 30min | 846 | 21.6
Manage Group | 24h 25min | 1559 | 161.1
Create Proposal | 7h | 596 | 54.9
Rate Proposal | 3h | 203 | 30.6
Filter View By Activities | 5h | 429 | 36.9
New Use Case |  | Calculated Time (min)
Change Account Password | 3h 45m | 225.1163 | 9.68
Change Account Email | 10h 34m | 634.4186 | 27.28
Delete Account | 5h 50m | 470.6977 | 20.24
Sum of old Ucs | 48h 55min | 3633 | 305.1
Sum Spent Time / Sum Points | 11.9076
Delete Group | RET | DET | FTR | Resulting Complexity |  |  | RET | DET | FTR
External Inputs | x | 1 | 1 | Low |  |  | - | delete button | group database
External Output | x | 1 | 2 | Low |  |  | - | confirmation popup | group database, account database
External Querie | x | 1 | 2 | Low |  |  | - | group edit button | group database, account database
Internal Logical Files | 2 | 6 | x | Low |  |  | group repository, membership repository | group id, group name, membership id, group, user, role | -
External Interface Files | 0 | 0 | x | Low |  |  | - |  | -
CRUD Manage Group | RET | DET | FTR | Resulting Complexity | Number of | Function Points | RET | DET | FTR
External Inputs | x | 25 | 2 | High |  |  | - | create group button, edit group button, group name input (2x), e-mail address (2x), grant admin role (3x) , add member button, cancel invitation (3x), confirm button (3x), cancel button (2x), revoke admin role, kick member, invite member, x-button (3x) | group database, account database
External Output | x | 3 | 2 | Low |  |  | - | create group popup, group settings, add member popup | group database, account database
External Querie | x | 1 | 1 | Low |  |  | - | change group | group database
Internal Logical Files | 2 | 6 | x | Low |  |  | group repository, membership repository | group id, group name, membership id, group, user, role | -
External Interface Files | 0 | 0 | x | Low |  |  | - | - | -
Create Proposal | RET | DET | FTR | Resulting Complexity | Number of | Function Points | RET | DET | FTR
External Inputs | x | 10 | 2 | Avg |  |  | - | add proposal button, activity type, proposal name, straße, stadt, plz, add groups, confirm button, cancel button, x-button | rating database, group database
External Output | x | 1 | 1 | Low |  |  | - | add proposal popup | rating database
External Querie | x | 1 | 2 | Low |  |  | - | rating list | rating database, group database
Internal Logical Files | 2 | 7 | x | Low |  |  | proposal repository, groupProposal repository | proposalld, activity type, name, address, groupProposalId, group, proposal | -
External Interface Files | 0 | 0 | x | Low |  |  | - | - | -
Rate Proposal | RET | DET | FTR | Resulting Complexity | Number of | Function Points | RET | DET | FTR
External Inputs | x | 1 | 1 | Low | 1 |  | - | thumbs rating | rating database
External Output | x | 1 | 2 | Low | 1 |  | - | best of rating list | rating database, group database
External Querie | x | 2 | 2 | Low | 1 |  | - | rating list, best of rating list | rating database, group database
Internal Logical Files | 3 | 11 | x | Low | 2 |  | rating repository, groupProposal repository, proposal repository | rating id, user, rating value, group proposal id, proposal id, name, address, activity type, group proposal id, group id, proposal id | -
External Interface Files | 0 | 0 | x | Low | 0 |  | - | - | -
Filter View by activites | RET | DET | FTR | Resulting Complexity | Number of | Function Points | RET | DET | FTR
External Inputs | x | 2 | 1 | Low | 2 |  | - | activity icons, reset button | rating database
External Output | x | 2 | 2 | Low | 2 |  | - | filtered best of rating list, filtered rating list | rating database, group database
External Querie | x | 2 | 2 | Low | 1 |  | - | best of rating list, rating list | rating databse, group database
Internal Logical Files | 3 | 11 | x | Low | 3 |  | rating repository, proposal repository, groupProposal repository | rating id, user, rating value, group proposal id, proposal id, name, address, activity type, group proposal id, group id, proposal id | -
External Interface Files | 0 | 0 | x | Low | 1 |  | - | - | -
Upcomming Ucs
Change Account password | RET | DET | FTR | Resulting Complexity | Number of | Function Points | RET | DET | FTR
External Inputs | x | 3 | 1 | Low | 0 |  | - | OldPassword, NewPassword, repeat NewPassword | User
External Output | x | 2 | 0 | Low | 1 |  | - | Modal | -
External Querie | x | 0 | 0 | Low | 0 |  | - | - | -
Internal Logical Files | 1 | 5 | x | Low | 1 | Estimation: | Controller | Username, Password, email, regDate, verifiied | -
External Interface Files | 0 | 0 | x | Low | 0 | 9.68 | - | - | -
Change Account email | RET | DET | FTR | Resulting Complexity | Number of | Function Points | RET | DET | FTR
External Inputs | x | 3 | 1 | Low | 0 |  | - | current password, old email, new email | User
External Output | x | 3 | 0 | Low | 3 |  | - | Email to old address, Email to new address, Modal | -
External Querie | x | 0 | 0 | Low | 0 |  | - | - | -
Internal Logical Files | 2 | 5 | x | Low | 2 | Estimation: | Change Email HTML, Controller | emailUUID, username, creationdate, verified, Email-Template | -
External Interface Files | 1 | 0 | x | Low | 1 | 27.28 | Email Interface | - | -
Delete Account | RET | DET | FTR | Resulting Complexity | Number of | Function Points | RET | DET | FTR
External Inputs | x | 2 | 1 | Low | 1 |  | - | Delete-btn, Confirmation Dialog | User
External Output | x | 2 | 0 | Low | 2 |  | - | Modal, Email | -
External Querie | x | 0 | 0 | Low | 0 |  | - | - | -
Internal Logical Files | 1 | 3 | x | Low | 1 | Estimation: | Controller | deleteUUID, username, creationdate, Email-Template | -
External Interface Files | 1 | 0 | x | Low | 1 | 20.24 | Email Interface | - | -